## Slide 1
City Council Study Session
March 13, 2018
Issaquah-Fall City Road
Project Update

## Slide 2: Meeting Agenda
Introductions
Schedule
Cost Implications
Factors Driving Cost
Actions Taken
Potential Cost Savings
Discussion
Direction from Council

## Slide 3: Project Overview – Congestion Relief & Safety

## Slide 4: Project Timeline

## Slide 5: Project Timeline

## Slide 6: Preliminary Estimates of Probable Construction $
Estimates include Construction Activities only
Conceptual Design Estimate (Nov., 2014) | $16.2 Million
Planning Level Estimate (Feb., 2017) | $20.3 Million
Preliminary Design Estimate (June, 2017) | $23.1 Million
Intermediate Design Estimate | $27.8 Million

## Slide 7: What Changed – Conceptual to Preliminary?
Changed Intersection Types to Roundabouts
Selected Bridge to Replace Culvert
Selected Landscaped Medians, Irrigation, and Bike Lane Buffers

## Slide 8: What Changed – Preliminary to Intermediate Design?
Increased Median Width – Adding Walls
Changed Drainage Design to Relocate Proposed Pond
Geotech Report – Poor Soils Impacts Bridge Foundations
Prosperity – Good Economy Increasing Unit Prices (FHWA Cost Indices) 7.8% Summer 2017

## Slide 9: What Have We Been Doing to Address Escalation?
Identified Major Cost Drivers
Conducted “Mini” Value Engineering Workshop in Lochner
Engaged Regional Contractor to Review Approach & Identify Potential Savings

## Slide 10: Potential Cost Savings
Focused on Major Cost Drivers
  Bridge Design & Construction Methods
  Reduced Roadway Cross Section
  Walls – Number & Type
  Intersections – Design Modifications

## Slide 11: Current Plan – Stay the Course
Cost | $26.2 Million
Schedule | 15 to 18 months For Bridge Construction
Issues | 1. Construction Estimate Over Budget 2. Keeps Roadway Open During Construction 3. Construction Estimate includes Potential Cost Savings from Redesign 4. Some Traffic Will Avoid Construction

## Slide 12: Preliminary Estimates of Probable Construction $
Estimates include Construction Activities only
Conceptual Design Estimate (Nov., 2014) | $16.2 Million
Planning Level Estimate (Feb., 2017) | $20.3 Million
Preliminary Design Estimate (June, 2017) | $23.1 Million
Intermediate Design Estimate | $27.8 Million
Current Plan – Stay the Course | $26.2 Million

## Slide 13: Alternative – Close the Road
Cost | $22.3 Million
Schedule | 6 to 7 months closure For bridge construction
Issues | 1. Reduced Construction Cost 2. Shorter Bridge Construction Schedule 3. Reduces Number of Impacted Trees 4. All Traffic Must Detour

## Slide 14: Preliminary Estimates of Probable Construction $
Estimates include Construction Activities only
Conceptual Design Estimate (Nov., 2014) | $16.2 Million
Planning Level Estimate (Feb., 2017) | $20.3 Million
Preliminary Design Estimate (June, 2017) | $23.1 Million
Intermediate Design Estimate | $27.8 Million
Current Plan – Stay the Course | $26.2 Million
Alternative – Close the Road | $22.3 Million

## Slide 15: Funding
Transportation Improvement Board
  2017 Application
    $5M Request
    Missed by One Point
    “Shovel Readiness”
  2018 Potential Application
    Due, August of 2018
    Award, November of 2018
    Funds Available, January of 2019

## Slide 16: Next Steps
Looking For Council Direction to:
  Stay the Course with Roadway Design Modifications, or
  Approval to Close the Roadway for Bridge Construction

## Slide 17: Discussion